## May Metrics
Project | Assigned Date | Type | Completed | Urgent | Non Technical / Partial Tech Completion
PTI - PPA | QC Notification Date | Pre-Production/Annual Compliance | QC Completed? | Urgent?
277621 - 367537 - KPMG Asset Management Platform | 2020-05-04 | pre-prod | Yes | No
363907 - 363908 - Symantec DeepSight | 2020-05-05 | pre-prod | Yes | No
299497 - 368817 - CrashPlan | 2020-05-04 | pre-prod | Yes | No
358436 - 371370 - Gateway BPM | 2020-05-06 | pre-prod | Yes | Yes
318339 - 360529 - Tableau | 2020-05-07 | annual | Yes | No
316464 - 364160 - Transport Commitment Management | 2020-05-06 | annual | Yes | No
344319 – 354257 - Kira Systems | 2020-05-11 | pre-prod | Yes | No
303011- 371186-CVent SSO Validation (Concur Integration) | 2020-05-13 | annual | Yes | No
287706 - 364346 - SAP Fiori TimeEntry - MyTimeSGC 2020 | 2020-05-15 | annual | Yes Non Techical | No | No Tech
369782 - 369801 - KPMG One (AWS-API) | 2020-05-15 | pre-prod | Yes Non Techical | No | No Tech
369445 - 369551 - KPMG One (AWS-Android) | 2020-05-15 | pre-prod | Yes Non Techical | No | No Tech
364111 - 372237 - Digital Gateway | 2020-05-14 | pre-prod | Yes | Yes
364670 - 368366 - KeySurvey | 2020-05-18 | pre-prod | Yes | No
316354 - 369627 - CLO Automation Tool | 2020-05-21 | annual | Yes | Yes
287709 - 365654 - KCentral (Firmwide & Others) | 2020-05-15 | annual | Yes | No
363169 - 363172 - Dark Web Monitoring | 2020-05-21 | pre-prod | Yes | No
PPA - 370809 Purple Team: KPMGSPARK | 2020-05-20 | Network | Yes | Yes
365592 – 365627 – Broadcom Support Portal | 2020-05-25 | pre-prod | Yes | No
QC Annual | QC Annual Completed | QC Pre-Prod | QC Pre-Prod Completed | QC - Pre-Prod Urgent | QC Pre-Prod Urgent completed | Network | Network Completed
6 | 5 | 11 | 9 | 2 | 2 | 1 | 1
83.33% | 81.82% |  |  | 100% |  | 100%
Completed | Completed |  |  | Completed |  | Complete
Overall Percentage Completed (Annual and Pre-Prod Overall average) |  | Annual | No Tech | Pre-Prod | No Tech
83.33% |  | 6 | 1 | 11 | 2
Actual Percentage of Annual Completed Technical QC
83.33%
Actual Percentage of Pre-Prod Completed Technical QC
81.82%
Actual Total Technical Percentage Completed:
82.35%
|  | Accutal Percentage of Annual Non Technical QC |  |  | Actual Percentage of Pre-Prod NonTechnical QC
|  | 16.67% |  |  | 18.18%
Story 1: Completed vs not Completed
| Jan | Feb | Mar | April | May
End to End Completed QC | 8 | 13 | 12 | 13 | 14
Non Technical/No QC | 3 | 6 | 3 | 7 | 3
Story 2: Missed Findings
| Jan | Feb | March | April | May
Technical Missed Findings | 4 | 9 | 9 | 4 | 3
Processed Miss Finding | 7 | 15 | 8 | 11 | 7
Story 3: Limitations
| Jan | Feb | March | April | May
Head Count | 3 | 2 | 3 | 4 | 1
Access Issues | 0 | 2 | 1 | 1 | 0
Accounts | 0 | 1 | 1 | 1 | 0
Mobile | 0 | 1 | 0 | 1 | 2
Network Pentest assistance |  |  | 1 | 4 | 1

## Missed Findings
Missed Findings
Project Name | Test Type | Additional Findings | Proposed Risk | Final Risk | Comments
287706 - 364346 - SAP Fiori TimeEntry - MyTimeSGC 2020 | annual | Untested Functunality | High | Hgh | The applciation has web based findings but the burp log does not show any web based teting. Unsure how to validate the findings with no factual evidence.
287706 - 364346 - SAP Fiori TimeEntry - MyTimeSGC 2020 | annual | Missing Directory Listing | High | High | Directory listing not provided
364670 - 368366 - KeySurvey | pre-prod | Cross Site Sripting | High | High | The application seemed to go through another pentest which caused numerous stored XSS after we completed testing. The scope as limited. The vendors third party that did the tests did not list xss in its findings.
Total Missed Findings | Total Added to reports | Total need review of internal process |  |  | Total Not added to Reports
3 | 3 |  |  |  | 2
Total Missed by Vendor
Blueinfy | 1
TCS | 2
Total Missed by Category
Admin Port Open | 0
Authentication Bypass | 0
Missing Directory Listing | 1
XSS | 1
Untested Functionality | 1

## Process Findings
Process Findings
Project Name | Test Type | Process Finding | Comments
318339 - 360529 - Tableau | annual | Missing Walk Through | TCS said it was damaged. They need to have a better solution and prepare for potential lost.
287706 - 364346 - SAP Fiori TimeEntry - MyTimeSGC 2020 | annual | Scoping Document | Scope says complete yet testers said the cloud portion was out of scope.
287706 - 364346 - SAP Fiori TimeEntry - MyTimeSGC 2020 | annual | Missing Directory Listing
287706 - 364346 - SAP Fiori TimeEntry - MyTimeSGC 2020 | annual | Appscan | Appscan Missing
316354 - 369627 - CLO Automation Tool | annual | Nmap | Nmap Missing
287709 - 365654 - KCentral (Firmwide & Others) | annual | Nmap | They did not upload all the required files which caused a false positive on the nmap. Once uploaded nmap was fine.
363169 - 363172 - Dark Web Monitoring | pre-prod | Scoping Document | Multiple fields missing
365592 – 365627 – Broadcom Support Portal | pre-prod | Scoping Document
365592 – 365627 – Broadcom Support Portal | pre-prod | Incorrect Risk Rating | Incorrect Risk rating for SSL TLS finding
334623 - 349925 - TAX Intelligent Automation Cloud | pre-prod | Access Issues | Accounts would not work even in incognito mode could not test.
369782 - 369801 - KPMG One (AWS-API) | pre-prod | Missing Directory Listing
Total Missed by Vendor
Blueinfy | 3
TCS | 6
Total Issues by Type:
Missing Directory Listing | 1
Missing Walk Through | 1
Scoping Document | 3 | Error in calc should be 2
Burp | 0
Appscan | 1
Access Issues | 0
Incorrect Risk Rating | 1
Accounts | 0
Final Report | 0
Nmap Missing / issues | 2

## Uncompleted
Project | Assigned Date | Type | Completed | Urgent | Reason | Comments
287706 - 364346 - SAP Fiori TimeEntry - MyTimeSGC 2020 | 2020-05-15 | annual | Yes Non Techical | No | Mobile
369782 - 369801 - KPMG One (AWS-API) | 2020-05-15 | pre-prod | Yes Non Techical | No | Resource
369445 - 369551 - KPMG One (AWS-Android) | 2020-05-15 | pre-prod | Yes Non Techical | No | Mobile
Top reasons for May
Resource | 1
Account issues | 0
Mobile | 2
Access Issues | 0
End of Month | 0

## May-Raw
PTI - PPA | QC Notification Date | Pre-Production/Annual Compliance | Start Date QC | End Date QC | QC Completed? | Urgent? | Additional Findings Identified? | Process Review Findings | Total # of Identified Findings | Application Size (S/M/L) | Additional Finding Details / Comment
277621 - 367537 - KPMG Asset Management Platform | 2020-05-04 | pre-prod | 2020-05-04 | 2020-05-06 | Yes | No |  |  |  |  | Process Status Appscan Ok Burp Ok Checklist Ok Directory Listing Ok Final Report Ok Walkthrough Ok Scoping Document Ok Accounts Ok Findings Ok
363907 - 363908 - Symantec DeepSight | 2020-05-05 | pre-prod | 2020-05-07 | 2020-05-08 | Yes | No |  |  |  |  | Process Status Appscan Ok Burp Ok Checklist Ok Directory Listing NA Final Report OK Walkthrough OK Scoping Document OK Accounts OK Findings OK
299497 - 368817 - CrashPlan | 2020-05-04 | pre-prod | 2020-05-07 | 2020-05-08 | Yes | no |  |  |  |  | Process Status Appscan Ok Burp Ok Checklist Ok Directory Listing NA Final Report OK Walkthrough OK Scoping Document OK Accounts OK Findings OK I agree with leaving the sensitive info as a high or at least a medium.
358436 - 371370 - Gateway BPM | 2020-05-06 | pre-prod | 2020-05-05 | 2020-05-08 | Yes | Yes |  |  |  |  | Process Status Appscan Ok Burp Ok Checklist Ok Directory Listing Ok Final Report OK Walkthrough OK Scoping Document OK Accounts OK Findings OK
318339 - 360529 - Tableau | 2020-05-07 | annual | 2020-05-08 | 2020-05-11 | Yes | No |  | x |  |  | Process Status Appscan Ok Burp Ok Checklist Ok Directory Listing Ok Final Report Ok Walkthrough Missing : seems to be the system32 directory of the OS Scoping Document Ok Accounts Ok Findings Ok
316464 - 364160 - Transport Commitment Management | 2020-05-06 | annual | 2020-05-11 | 2020-05-12 | Yes | No |  |  |  |  | Process Status Appscan Ok Burp Ok Checklist Ok Directory Listing Ok Final Report Ok Walkthrough Ok Scoping Document Ok Accounts Ok Only had one account for the 12 roles, not tester fault Findings Ok
344319 – 354257 - Kira Systems | 2020-05-11 | pre-prod | 2020-05-12 | 2020-05-13 | Yes | No |  |  |  |  | Process Status Appscan Ok Burp Ok Checklist Ok Directory Listing Ok Final Report Ok Walkthrough Ok Scoping Document Ok Accounts Ok Findings Ok Directory : Third party site
303011- 371186-CVent SSO Validation (Concur Integration) | 2020-05-13 | annual | 2020-05-14 | 2020-05-15 | yes | no |  |  |  |  | Process Status Appscan Ok Burp Ok Checklist Ok Directory Listing NA Third party Final Report Ok Walkthrough Ok Scoping Document Ok Accounts Ok Findings Ok Question on finding 4 What is the value of the data in the url. Is that unique per person and does it change? Tried to do ome fuzzing of it but assumed further testign was out of scope due to the limited scope of test.
287706 - 364346 - SAP Fiori TimeEntry - MyTimeSGC 2020 | 2020-05-15 | annual | 2020-05-18 | 2020-05-18 | Yes Non Techical | No | x | x |  |  | Process Status Appscan Missing: Mobile app but you have web findings, you did a nmap of the IP but no appscan? Burp Burp log is 15kb. The burp log shows capture of login page but no further testing if the application outside of the app. The report has web findings but no further testing. Was none of the 2019 testing retested? Checklist Ok Directory Listing Missing: Noted in the report Final Report Ok Walkthrough Missing Scoping Document Ok Accounts Ok Findings Ok Question validity of testing based on data provided. ADD a HIGH for untested functionality. and a MISSED dir listing.
369782 - 369801 - KPMG One (AWS-API) | 2020-05-15 | pre-prod | 2020-05-18 | 2020-05-18 | Yes Non Techical | No
369445 - 369551 - KPMG One (AWS-Android) | 2020-05-15 | pre-prod | 2020-05-19 | 2020-05-19 | Yes Non Techical | No |  | x |  |  | Process Status Appscan NA Burp Missing: looks to have a api as well Checklist Ok Directory Listing NA Final Report Ok Walkthrough OK Scoping Document Ok Accounts Ok Findings Ok
364111 - 372237 - Digital Gateway | 2020-05-14 | pre-prod | 2020-05-14 | 2020-05-19 | Yes | Yes |  |  |  |  | Process Status Appscan Ok Burp Ok Checklist Ok Directory Listing OK Final Report Ok Walkthrough Ok Scoping Document Ok Accounts Ok Findings Ok
364670 - 368366 - KeySurvey | 2020-05-18 | pre-prod | 2020-05-20 | 2020-05-21 | Yes | No | x |  |  |  | Process Status Appscan Ok Burp Ok Checklist Ok Directory Listing OK Final Report Ok Walkthrough Ok Scoping Document Ok Accounts Ok Findings Ok : Additional finding for XSS
316354 - 369627 - CLO Automation Tool | 2020-05-21 | annual | 2020-05-22 | 2020-05-26 | Yes | Yes |  | x |  |  | 5/26/2020: ML QC Completed Process Status Appscan Ok Burp Ok Checklist Ok Directory Listing OK Final Report Ok Walkthrough Ok Scoping Document Ok Accounts Ok Nmap: Missing Findings Ok
287709 - 365654 - KCentral (Firmwide & Others) | 2020-05-15 | annual | 2020-05-19 | 2020-05-22 | Yes | No |  | x |  |  | 5/22/2020: ML QC Compelted Process Status Appscan Ok Burp Ok Checklist Ok Directory Listing OK Final Report Ok Walkthrough Ok Scoping Document Ok Accounts Ok Nmap: Why are we not scanning all ports, looks like tester specified port ranges. Findings Ok
363169 - 363172 - Dark Web Monitoring | 2020-05-21 | pre-prod | 2020-05-27 | 2020-05-28 | Yes | No |  | x |  |  | 5/28/2020: ML QC Completed Process Status Appscan Ok Burp Ok Checklist Ok Directory Listing OK Final Report Ok Walkthrough Ok Scoping Document Multiple data points missing: No DC rating selected. Any limited scope is marked as no, however later in doc says limited to sso only. Accounts Ok Findings Ok
365592 – 365627 – Broadcom Support Portal | 2020-05-25 | pre-prod | 2020-05-27 | 2020-05-28 | Yes | No |  | x |  |  | Process Status Appscan Ok Burp Ok Checklist Ok Directory Listing OK Final Report Ok Walkthrough Ok Scoping Document multiple data points missing: No DC rating selected. Accounts Ok Findings Ok

## May Stripped
PTI - PPA | QC Notification Date | Pre-Production/Annual Compliance | QC Completed? | Urgent?
277621 - 367537 - KPMG Asset Management Platform | 2020-05-04 | pre-prod | Yes | No
363907 - 363908 - Symantec DeepSight | 2020-05-05 | pre-prod | Yes | No
299497 - 368817 - CrashPlan | 2020-05-04 | pre-prod | Yes | no
358436 - 371370 - Gateway BPM | 2020-05-06 | pre-prod | Yes | Yes
318339 - 360529 - Tableau | 2020-05-07 | annual | Yes | No
316464 - 364160 - Transport Commitment Management | 2020-05-06 | annual | Yes | No
344319 – 354257 - Kira Systems | 2020-05-11 | pre-prod | Yes | No
303011- 371186-CVent SSO Validation (Concur Integration) | 2020-05-13 | annual | yes | no
287706 - 364346 - SAP Fiori TimeEntry - MyTimeSGC 2020 | 2020-05-15 | annual | Yes Non Techical | No
369782 - 369801 - KPMG One (AWS-API) | 2020-05-15 | pre-prod | Yes Non Techical | No
369445 - 369551 - KPMG One (AWS-Android) | 2020-05-15 | pre-prod | Yes Non Techical | No
364111 - 372237 - Digital Gateway | 2020-05-14 | pre-prod | Yes | Yes
364670 - 368366 - KeySurvey | 2020-05-18 | pre-prod | Yes | No
316354 - 369627 - CLO Automation Tool | 2020-05-21 | annual | Yes | Yes
287709 - 365654 - KCentral (Firmwide & Others) | 2020-05-15 | annual | Yes | No
363169 - 363172 - Dark Web Monitoring | 2020-05-21 | pre-prod | Yes | No
365592 – 365627 – Broadcom Support Portal | 2020-05-25 | pre-prod | Yes | No